## Time Log
Time Log
• Add an entry each time you worrk on the project
• Example: begin working June 10 at 12:30 pm, type: 6/10 12:30 p
• Interrupt time is time you took a break. Leave blank if none
• Interrupt time example. Suppose you take a break for 15 min, type: 0:15
• The highlighted columns are automatically calculated and should not be editted (generally). Contact me if there is a problem
• If you delete a row, it will probably mess up the calculations. In that case you'll need to copy the formulas back down the sheet.
Automatically Calculated
Initials | Beg Date/Time | End Date/Time | Int.Time | Tot Time | Run Total | Act Code | Description of Activity
ch | 2024-09-24 11:00 | 2024-09-24 12:20 |  | 0.055556 | 0.055556 | D | Used project lab day to plan and discuss the project
wa | 2024-09-24 11:00 | 2024-09-24 14:10 | 0:10 | 0.125 | 0.18056 | D | planned meeting times, discussed requirements and began to outline project
mu | 2024-09-24 11:00 | 2024-09-24 12:20 |  | 0.055556 | 0.23611 | D | Discussed meeting times, project requirements, and began class diagram
km | 2024-09-24 11:00 | 2024-09-24 12:20 |  | 0.055556 | 0.29167 | D | Discussed planning on project lab day
ch | 2024-10-17 11:00 | 2024-10-17 12:40 |  | 0.069444 | 0.36111 | D | Continued planning and started diagram
mu | 2024-10-17 11:00 | 2024-10-17 12:40 |  | 0.069444 | 0.43056 | D/C | Planning/worked on diagram and started on Gui
mu | 2024-10-21 19:00 | 2024-10-21 20:30 |  | 0.0625 | 0.49306 | C | Worked on gui and code for user story 1
ch | 2024-10-22 11:00 | 2024-10-22 15:20 | 0:30 | 0.15972 | 0.65278 | D/C | Tried to figure out push and worked on basic gui
mu | 2024-10-22 11:00 | 2024-10-22 12:20 |  | 0.055556 | 0.70833 | D/C | Pushed my code to github and worked on gui elements/code for user story 2
km | 2024-10-22 11:00 | 2024-10-22 12:20 |  | 0.055556 | 0.76389 | D/C | Discussed and planned on project lab day
km | 2024-10-22 18:30 | 2024-10-22 20:30 |  | 0.083333 | 0.84722 | O | Troubleshooting Git
km | 2024-10-24 08:30 | 2024-10-24 10:40 |  | 0.090278 | 0.9375 | D/C | Read through materials on data persistence
km | 2024-10-24 11:00 | 2024-10-24 12:50 |  | 0.076389 | 1899-12-31 00:20 | D/C/O | Project lab day, discussed requirements, pushed to GitHub, troubleshooting Git
ch | 2024-10-24 11:10 | 2024-10-24 16:30 | 1:15 | 0.17014 | 1899-12-31 04:25 | O | Troubleshooting issues with push and pull from github
km | 2024-10-24 14:00 | 2024-10-24 18:00 |  | 0.16667 | 1899-12-31 08:25 | O | Troubleshooting git
km | 2024-10-27 20:00 | 2024-10-27 21:45 |  | 0.072917 | 1899-12-31 10:10 | C/O | Worked on code for handling text files, troubleshooting IDE
km | 2024-10-28 17:00 | 2024-10-28 17:35 |  | 0.024306 | 1899-12-31 10:45 | O | Fixed IDE issue
mu | 2024-10-24 11:00 | 2024-10-24 14:00 |  | 0.125 | 1899-12-31 13:45 | O | Trying to fix issue with pulling from github
cm | 2024-09-24 11:00 | 2024-09-24 12:20 |  | 0.055556 | 1899-12-31 15:05 | D | Project lab day, discussed initial plans for project
cm | 2024-10-17 11:00 | 2024-10-17 12:20 |  | 0.055556 | 1899-12-31 16:25 | D | Project lab day, began diagram
cm | 2024-10-20 13:00 | 2024-10-20 14:30 |  | 0.0625 | 1899-12-31 17:55 | C | Created basic versions of item and auction classes
cm | 2024-10-22 11:00 | 2024-10-22 12:30 |  | 0.0625 | 1899-12-31 19:25 | C | Project lab day, continued to develop item and auction
cm | 2024-10-24 11:00 | 2024-10-24 12:20 |  | 0.055556 | 1899-12-31 20:45 | C | Project lab day, item at functional level, mild restructure of github design
mu | 2024-10-25 13:00 | 2024-10-25 14:00 |  | 0.041667 | 1899-12-31 21:45 | C | Finished gui/code for user story 2
mu | 2024-10-29 12:15 | 2024-10-29 13:30 |  | 0.052083 | 1899-12-31 23:00 | C | Worked on gui elements/code for user story 3
mu | 2024-10-29 19:30 | 2024-10-29 20:30 |  | 0.041667 | 1900-01-01 | C | Finished gui/code for user story 3
mu | 2024-10-30 13:00 | 2024-10-30 15:30 |  | 0.10417 | 1900-01-01 02:30 | C | Redesigned gui and added elements for user story 4
wa | 2024-10-17 11:00 | 2024-10-17 14:10 | 0:10 | 0.125 | 1900-01-01 05:30 | D | Planned and started to create UML diagram
wa | 2024-10-22 11:00 | 2024-10-22 14:10 | 0:10 | 0.125 | 1900-01-01 08:30 | D | Troubleshooting IDE, GITHUB
wa | 2024-10-24 09:00 | 2024-10-24 11:00 |  | 0.083333 | 1900-01-01 10:30 | D | Figuring out issues with IDE
wa | 2024-10-24 11:00 | 2024-10-24 14:10 | 0:10 | 0.125 | 1900-01-01 13:30 | D | Reviewing GUI, pushing/pulling from GITHUB
ch | 2024-10-29 12:15 | 2024-10-29 14:00 | 0:15 | 0.0625 | 1900-01-01 15:00 | D | Spent trying to figure out how to pull and run code from intellaJ
wa | 2024-10-24 13:00 | 2024-10-24 14:10 |  | 0.048611 | 1900-01-01 16:10 | D | Figuring out issues with IDE
wa | 2024-10-27 09:00 | 2024-10-27 12:30 |  | 0.14583 | 1900-01-01 19:40 | C | Creating GUI copy and adding sign in function, and pop up windows for functions
ch | 2024-10-31 11:45 | 2024-10-31 16:00 | 1:00 | 0.13542 | 1900-01-01 22:55 | D/C | Forgot how to pull code from github to eclipse/ worked on gui
wa | 2024-10-29 12:30 | 2024-10-29 14:10 |  | 0.069444 | 1900-01-02 00:35 | C | Fixed library issues, started to implement functions from TM GUI
wa | 2024-10-31 09:00 | 2024-10-31 10:30 |  | 0.0625 | 1900-01-02 02:05 |  | Finished combining TM GUI and my own
wa | 2024-10-31 11:45 | 2024-10-31 13:30 |  | 0.072917 | 1900-01-02 03:50 | C | Pushed to GITHUB and discussed roles for the weekend.
km | 2024-10-30 20:00 | 2024-10-30 22:46 |  | 0.11528 | 1900-01-02 06:36 | C/T/O | Coded and tested errors
km | 2024-10-31 10:00 | 2024-10-31 13:40 | 0:45 | 0.12153 | 1900-01-02 09:31 | C/T/O | Coded and worked on data persistence class and discussed plans
km | 2024-11-02 17:30 | 2024-11-02 21:30 |  | 0.16667 | 1900-01-02 13:31 | C/O | Worked on classes related to Auction class then troubleshot IDE again
wa | 2024-11-02 12:00 | 2024-11-02 14:10 |  | 0.090278 | 1900-01-02 15:41 | D | reviewed and messed with class notes and examples from 1302 on save/load data
wa | 2024-11-03 15:55 | 2024-11-03 19:00 |  | 0.12847 | 1900-01-02 18:46 | C/T | created save/ load class for system admin GUI
wa | 2024-11-03 19:00 | 2024-11-03 23:25 |  | 0.18403 | 1900-01-02 23:11 | C/T | added password and sign out function, tried to implement load/ save to registered user
km | 2024-11-03 14:00 | 2024-11-03 18:00 |  | 0.16667 | 1900-01-03 03:11 | C/T | Fixed errors in code with reading text files
wa | 2024-11-04 10:15 | 2024-11-04 11:50 |  | 0.065972 | 1900-01-03 04:46 | C | finished save / load registered user, created a credentials class to create and save usernames and passwords
ch | 2024-11-04 10:45 | 2024-11-04 15:15 | 1:15 | 0.13542 | 1900-01-03 08:01 | D/C | Added functions to the User class
mu | 2024-10-31 11:45 | 2024-10-31 13:40 |  | 0.079861 | 1900-01-03 09:56 | C | Pushed to git and discussed plans
mu | 2024-11-04 13:00 | 2024-11-04 15:30 |  | 0.10417 | 1900-01-03 12:26 | T | Wrote simple credentials text file and started to write system tests.
mu | 2024-11-04 17:00 | 2024-11-04 18:30 |  | 0.0625 | 1900-01-03 13:56 | C/D | Updated gui functions
km | 2024-11-04 17:00 | 2024-11-04 22:23 | 3:00 | 0.099306 | 1900-01-03 16:19 | D/C/O | Read on JUnit and started test class, pushed to Github
cm | 2024-10-19 11:00 | 2024-10-19 14:00 |  | 0.125 | 1900-01-03 19:19 | D/O | Troubleshooting with Github on personal computer
cm | 2024-10-29 12:15 | 2024-10-29 13:30 |  | 0.052083 | 1900-01-03 20:34 | D/C | Began to restructure Item and Auction
cm | 2024-10-31 10:45 | 2024-10-31 12:30 |  | 0.072917 | 1900-01-03 22:19 | D/C | Distinguished Auction from Item
cm | 2024-11-04 10:00 | 2024-11-04 13:00 | 1:00 | 0.083333 | 1900-01-04 00:19 | D/C | Further developed Auction, created User
cm | 2024-11-05 11:00 | 2024-11-05 12:45 |  | 0.072917 | 1900-01-04 02:04 | D/C/T | Mild development to Auction, began work on JUnit tests for Auction, Item
cm | 2024-11-02 13:00 | 2024-11-02 15:00 | 0:30 | 0.0625 | 1900-01-04 03:34 | C/O | Researched Tree Maps and other related methods to store bids
wa | 2024-11-05 11:00 | 2024-11-05 12:40 |  | 0.069444 | 1900-01-04 05:14 | C/O | Discussed Demo with team. Converted some methods to follow MVC
wa | 2024-11-05 13:30 | 2024-11-05 14:10 |  | 0.027778 | 1900-01-04 05:54 |  | Moved methods to follow MVC
mu | 2024-11-05 11:00 | 2024-11-05 13:00 |  | 0.083333 | 1900-01-04 07:54 | O/T | Try to fix issues in github and JUnit tests for commission/premium
ch | 2024-11-05 11:00 | 2024-11-05 12:20 |  | 0.055556 | 1900-01-04 09:14 | C/O | Was used figuring out push issues in github
wa | 2024-11-06 11:00 | 2024-11-06 12:00 |  | 0.041667 | 1900-01-04 10:14 | O | compiling project onto main branch
cm | 2024-11-06 10:00 | 2024-11-06 12:40 | 0:30 | 0.090278 | 1900-01-04 12:24 | C/T | Mild alteration to User/Auction/Item, realized test classes for each
ch | 2024-11-06 10:50 | 2024-11-06 18:30 | 4:00 | 0.15278 | 1900-01-04 16:04 | D/C/P | Worked on class diagram along with some presenting
cm | 2024-11-06 16:20 | 2024-11-06 18:30 |  | 0.090278 | 1900-01-04 18:14 | D/P | Discussed final considerations before end of sprint 1
mu | 2024-11-06 16:00 | 2024-11-06 18:30 |  | 0.10417 | 1900-01-04 20:44 | P/O | Switched ide and discussed how we will move forward after sprint 1
km | 2024-11-06 11:00 | 2024-11-06 12:00 |  | 0.041667 | 1900-01-04 21:44 | O | Fixed merge issue and updated main
km | 2024-11-06 16:00 | 2024-11-06 18:30 |  | 0.10417 | 1900-01-05 00:14 | O | Met as group to discuss presentations, git issues, requirements, plans, etc
km | 2024-11-06 19:15 | 2024-11-06 22:30 |  | 0.13542 | 1900-01-05 03:29 | O | Resolved and restored old work on main after branch issue
wa | 2024-11-06 13:00 | 2024-11-06 14:15 |  | 0.052083 | 1900-01-05 04:44 | O | merging and downloading branches
wa | 2024-11-07 09:30 | 2024-11-07 11:30 |  | 0.083333 | 1900-01-05 06:44 | O | prepped for demo
ch | 2024-11-07 09:30 | 2024-11-07 11:30 |  | 0.083333 | 1900-01-05 08:44 | O/P | Final touches for demo
km | 2024-11-07 09:10 | 2024-11-07 11:30 |  | 0.097222 | 1900-01-05 11:04 | O | Demo prep
cm | 2024-11-07 09:30 | 2024-11-07 11:30 | 0:20 | 0.069444 | 1900-01-05 12:44 | O | Final Preparations for demo
mu | 2024-11-07 09:30 | 2024-11-07 11:30 |  | 0.083333 | 1900-01-05 14:44 | O | Prepped for split 1 demo
km | 2024-11-07 14:00 | 2024-11-07 14:30 |  | 0.020833 | 1900-01-05 15:14 | O | Opened pull request to clean/fix main
ch | 2024-11-11 12:30 | 2024-11-11 13:30 |  | 0.041667 | 1900-01-05 16:14 | O | Setup IntelliJ
ch | 2024-11-12 11:45 | 2024-11-12 13:55 | 0:15 | 0.079861 | 1900-01-05 18:09 | O/C | Finished setting up IntelliJ and added functionality to User login
mu | 2024-11-12 11:45 | 2024-11-12 14:00 |  | 0.09375 | 1900-01-05 20:24 | O | Tried to resolve issue with junit testing
km | 2024-11-12 11:45 | 2024-11-12 13:45 |  | 0.083333 | 1900-01-05 22:24 | O/T | Junit
mu | 2024-11-13 15:00 | 2024-11-13 17:00 |  | 0.083333 | 1900-01-06 00:24 | C | Wrote gui elements for us 6, 10, 11, 12, 13.
cm | 2024-11-09 14:00 | 2024-11-09 17:00 |  | 0.125 | 1900-01-06 03:24 | O/D | Setup IntelliJ, researched threading for time keeping
cm | 2024-11-12 11:45 | 2024-11-12 12:40 |  | 0.038194 | 1900-01-06 04:19 | D/C | Changed Auction/Item to allow for use of User
cm | 2024-11-13 17:00 | 2024-11-13 18:30 |  | 0.0625 | 1900-01-06 05:49 | C | Changed Auction to better fit rubric requirements
cm | 2024-11-14 10:50 | 2024-11-14 12:30 |  | 0.069444 | 1900-01-06 07:29 | C/D | Further improvements to Auction/User
ch | 2024-11-14 10:40 | 2024-11-14 13:15 | 0:15 | 0.097222 | 1900-01-06 09:49 | C/D | Added some basic functinality to User GUI
km | 2024-11-14 11:00 | 2024-11-14 13:15 |  | 0.09375 | 1900-01-06 12:04 | C/O | Restructured files, added user variable to main
km | 2024-11-15 20:00 | 2024-11-15 21:40 |  | 0.069444 | 1900-01-06 13:44 | D/C | Reviewed MVC and improved AuctionManager
km | 2024-11-16 17:10 | 2024-11-16 21:00 | 0:45 | 0.12847 | 1900-01-06 16:49 | D/C | Worked on auction classes, validation methods, GUI
mu | 2024-11-14 11:10 | 2024-11-14 13:10 |  | 0.083333 | 1900-01-06 18:49 | D | Working on a way to implement classes into gui
km | 2024-11-18 16:20 | 2024-11-18 22:25 | 0:45 | 0.22222 | 1900-01-07 00:09 | D/T/C/O | Created AuctionValidator class, test class, exception classes for errors, worked on auction classes
mu | 2024-11-19 11:00 | 2024-11-19 12:40 |  | 0.069444 | 1900-01-07 01:49 | D/C | Worked on changing gui and premium controller class for better MVC.
mu | 2024-11-19 18:30 | 2024-11-19 20:30 |  | 0.083333 | 1900-01-07 03:49 | D/C/T | Finished up changes to gui/premium controller and updated junit test for premiumContoller
km | 2024-11-19 11:00 | 2024-11-19 12:40 |  | 0.069444 | 1900-01-07 05:29 | C/O | Discussed implementation of several user stories, group planning, worked on fixing auctionvalidator
km | 2024-11-19 20:00 | 2024-11-19 22:50 |  | 0.11806 | 1900-01-07 08:19 | C/T/O | Worked on auctionvalidator and test classes, discussed reworking premium controller with groupmate
mu | 2024-11-20 18:00 | 2024-11-20 20:00 |  | 0.083333 | 1900-01-07 10:19 | D/C/O | Tried to figure out a better way to implement controller classes into gui (MVC)
ch | 2024-11-19 11:00 | 2024-11-19 12:40 |  | 0.069444 | 1900-01-07 11:59 | D/C | Worked on adding a function that allows sellers to assign categories to items (Has been //)
km | 2024-11-21 11:00 | 2024-11-21 12:40 |  | 0.069444 | 1900-01-07 13:39 | D/C | Researched time and date classes and methods
km | 2024-11-21 13:30 | 2024-11-21 16:21 | 0:40 | 0.090972 | 1900-01-07 15:50 | D/C/T | Worked on auction manager, controller, validator, gui functions
mu | 2024-11-21 11:00 | 2024-11-21 12:40 |  | 0.069444 | 1900-01-07 17:30 | D/C | Changed gui/commission contoller for better MVC.
mu | 2024-11-21 18:00 | 2024-11-21 19:00 |  | 0.041667 | 1900-01-07 18:30 | C/T | Updated junit test for commissionController
km | 2024-11-21 19:00 | 2024-11-21 20:50 | 0:10 | 0.069444 | 1900-01-07 20:10 | D/C/T | Added date validation, wrote test methods, researched a bit on threading
km | 2024-11-22 17:00 | 2024-11-22 20:00 |  | 0.125 | 1900-01-07 23:10 | D/C/T | Tweaked validator, experimented with time and clock classes and threading, added auction constructor
km | 2024-11-26 09:00 | 2024-11-26 16:15 | 3:00 | 0.17708 | 1900-01-08 03:25 | D/C/O | Worked on and off on gui for bidding, loading saved auctions from file, delineated group plans
mu | 2024-12-02 15:00 | 2024-12-02 17:30 | 1:00 | 0.0625 | 1900-01-08 04:55 | D/C | Added tab pane and small elements to gui
cm | 2024-11-15 13:00 | 2024-11-15 15:00 | 0:30 | 0.0625 | 1900-01-08 06:25 | D/C | Research into Item/User ID Generation
cm | 2024-11-17 11:00 | 2024-11-17 12:30 |  | 0.0625 | 1900-01-08 07:55 | D/C | Changed AuctionManager, Auction.endAuction fixed to not require an item input
cm | 2024-11-19 11:00 | 2024-11-19 12:45 |  | 0.072917 | 1900-01-08 09:40 | D/C/T | Changed Item constructor to include ID generation, User/Item Manager classes added, Auction improved, AuctionTest improved
cm | 2024-11-22 10:00 | 2024-11-22 14:00 | 0:30 | 0.14583 | 1900-01-08 13:10 | D | Research into threading to track time for automated auction ending
cm | 2024-11-25 10:00 | 2024-11-25 15:00 | 1:00 | 0.16667 | 1900-01-08 17:10 | C/T | Created UserController, ItemController, fixed Item constructor to work with new code generation, improved AuctionTest, Slight change to ItemManager
cm | 2024-11-30 11:00 | 2024-11-30 15:00 | 0:30 | 0.14583 | 1900-01-08 20:40 | D | Continued research into threading,
cm | 2024-12-01 12:00 | 2024-12-01 14:00 |  | 0.083333 | 1900-01-08 22:40 | D/C | Changed AuctionManger to include ScheduledExectutorService for time keeping, fix Auction checkDate to have slightly different logic. Changed Main.java to include new scheduler shutdown function. Changed User constructor to conform with new ID generation
cm | 2024-12-03 11:00 | 2024-12-03 12:45 |  | 0.072917 | 1900-01-09 00:25 | D | With due date approaching, discussed which US were to be prioritized or discarded with group
cm | 2024-12-01 16:30 | 2024-12-01 18:30 |  | 0.083333 | 1900-01-09 02:25 | D | IntelliJ was not updated local branch to conform with Github branch, required troubleshooting
ch | 2024-12-03 11:00 | 2024-12-03 13:25 |  | 0.10069 | 1900-01-09 04:50 | D/C/O | Discused US's along with troubleshooting some minor errors
km | 2024-12-03 11:00 | 2024-12-03 13:37 |  | 0.10903 | 1900-01-09 07:27 | D/C/O | More discussion on remaining user stories, requirements, plans, updated main with bidding and fixed null error
mu | 2024-12-03 11:00 | 2024-12-03 13:35 |  | 0.10764 | 1900-01-09 10:02 | D/O | Discussed user stories and plans since due date is approaching.
mu | 2024-12-03 22:00 | 2024-12-03 23:30 |  | 0.0625 | 1900-01-09 11:32 | D/C | Tried to create report class to generate sellers report
km | 2024-12-04 11:20 | 2024-12-04 12:10 |  | 0.034722 | 1900-01-09 12:22 | D/O | Discussed issues with recently pushed code
km | 2024-12-04 18:00 | 2024-12-04 21:00 | 0:40 | 0.097222 | 1900-01-09 14:42 | D/C/T/O | Reviewed overall work and assigned new tasks, added auctionmanager tests and some code for winning bid
mu | 2024-12-04 14:00 | 2024-12-04 16:30 |  | 0.10417 | 1900-01-09 17:12 | D/C | Added elements from user to registered user bidding tab and worked on US-14 (set date/time)
mu | 2024-12-04 19:00 | 2024-12-04 21:30 |  | 0.10417 | 1900-01-09 19:42 | D/C | Worked on US-15 (Resume real time) and bid manager junit test.
km | 2024-12-06 13:30 | 2024-12-06 17:30 | 1:00 | 0.125 | 1900-01-09 22:42 | D/C/O | Fixed issues with reading and saving data and showing auction info, added bid usernames
km | 2024-12-08 17:00 | 2024-12-08 21:30 | 0:30 | 0.16667 | 1900-01-10 02:42 | C/T/O | Worked on finishing show my bids and show my auctions
cm | 2024-12-05 11:00 | 2024-12-05 12:15 |  | 0.052083 | 1900-01-10 03:57 | D | Discussed final delegation of work before the due date
cm | 2024-12-04 10:00 | 2024-12-04 16:00 | 3:00 | 0.125 | 1900-01-10 06:57 | D/C | Worked on condensing User, removing unnecessary JUnit tests, and some compilation issue resolution
cm | 2024-12-05 17:00 | 2024-12-05 20:00 |  | 0.125 | 1900-01-10 09:57 | C/O | In some way broke my IDE, troubleshooting required but not successful so far
cm | 2024-12-06 16:00 | 2024-12-06 19:00 |  | 0.125 | 1900-01-10 12:57 | C/O | Couldn't properly fix IDE, eventually did a clean reinstall which solved issue
cm | 2024-12-07 13:00 | 2024-12-07 14:30 |  | 0.0625 | 1900-01-10 14:27 | D/C | Fixed Test Methods in AuctionTest
cm | 2024-12-08 15:00 | 2024-12-08 16:00 |  | 0.041667 | 1900-01-10 15:27 | D/C | Minor readjustments to AuctionTest to reflect current version of Auction
mu | 2024-12-05 11:00 | 2024-12-05 13:05 |  | 0.086806 | 1900-01-10 17:32 | D/C | Discussed with group on plans regarding project and meeting up for video, worked on us-15
km | 2024-12-09 13:30 | 2024-12-09 16:30 |  | 0.125 | 1900-01-10 20:32 | D/C | Discussed project with groupmate, corrected duplicate auction issue, added bid history
mu | 2024-12-09 14:30 | 2024-12-09 18:30 | 0:30 | 0.14583 | 1900-01-11 00:02 | D/C/O | Fixed issue in IDE with merging, discussed project with group member, looked into threading more.
mu | 2024-12-09 21:00 | 2024-12-09 22:00 |  | 0.041667 | 1900-01-11 01:02 | T | Added a few system tests.
km | 2024-12-10 01:30 | 2024-12-10 03:30 |  | 0.083333 | 1900-01-11 03:02 | D/C/T | Added to test classes, cleaned up code, fixed calculate time, fixed some data input
wa | 2024-11-12 11:45 | 2024-11-12 13:45 |  | 0.083333 | 1900-01-11 05:02 | O/T | Junit
wa | 2024-11-14 11:00 | 2024-11-14 14:10 | 0:10 | 0.125 | 1900-01-11 08:02 | C | implemented user ID, GUI
wa | 2024-11-19 11:00 | 2024-11-19 14:10 | 0:10 | 0.125 | 1900-01-11 11:02 | C | user ID creation
wa | 2024-11-21 11:00 | 2024-11-21 14:10 | 0:10 | 0.125 | 1900-01-11 14:02 | D/C | discussed plans to finish US and how to distinguish auctions
wa | 2024-11-23 10:00 | 2024-11-23 16:00 | 1:00 | 0.20833 | 1900-01-11 19:02 |  | User GUI implications
wa | 2024-11-26 11:00 | 2024-11-26 11:45 |  | 0.03125 | 1900-01-11 19:47 | C | Junit testing
wa | 2024-11-30 13:30 | 2024-11-30 20:00 | 1:30 | 0.20833 | 1900-01-12 00:47 | C | implemented error catching on log-in and account creation
ch | 2024-12-04 13:00 | 2024-12-04 17:30 |  | 0.1875 | 1900-01-12 05:17 | D | Breifly reveiwed relationships between classes
ch | 2024-12-05 11:00 | 2024-12-05 17:30 | 0:20 | 0.25694 | 1900-01-12 11:27 | C | Updated code and added some minor fixes to get a pull from main to run
ch | 2024-12-06 11:00 | 2024-12-06 15:00 |  | 0.16667 | 1900-01-12 15:27 | C | Solved a conflict in my local code I found while pulling from gethub
ch | 2024-12-07 22:00 | 2024-12-08 02:00 | 0:30 | 0.14583 | 1900-01-12 18:57 | D | Looked over classes for their relationships to one another
ch | 2024-12-09 14:00 | 2024-12-09 22:30 | 0:15 | 0.34375 | 1900-01-13 03:12 | D,P | Worked on and made the bulk of the class diagram
wa | 2024-12-01 13:00 | 2024-12-01 22:00 | 0:45 | 0.34375 | 1900-01-13 11:27 | C/T | created, implemented, tested duplicate username prevention
mu | 2024-12-10 11:30 | 2024-12-10 14:00 |  | 0.10417 | 1900-01-13 13:57 | T/P/O | Updated systems test, dicussed the final project with groupmates
cm | 2024-12-10 12:20 | 2024-12-10 14:00 |  | 0.069444 | 1900-01-13 15:37 | T/P/O | Updated AuctionTest, discussed final project considerations and preparations for video recording
cm | 2024-12-09 10:00 | 2024-12-09 13:00 | 2:00 | 0.041667 | 1900-01-13 16:37 | D/C | Improved AuctionManager.checkDates(), Auction.checkDate(), IDE required further troubleshooting
km | 2024-12-10 11:00 | 2024-12-10 21:40 | 3:00 | 0.31944 | 1900-01-14 00:17 | D/C/T/O | Discussed remaining work with group, planned, implemented rest of user stories
mu | 2024-12-10 22:30 | 2024-12-10 23:00 |  | 0.020833 | 1900-01-14 00:47 | T | Added system tests
wa | 2024-12-10 11:00 | 2024-12-10 14:00 | 0:45 | 0.09375 | 1900-01-14 03:02 | T/P/O | Discussed remaining work with group, planned presentation
cm | 2024-12-11 09:00 | 2024-12-11 12:15 |  | 0.13542 | 1900-01-14 06:17 | D/T/P | Final adjustments to US, video, etc.
mu | 2024-12-11 08:45 | 2024-12-11 12:15 |  | 0.14583 | 1900-01-14 09:47 | D/T/P | Final adjustments to US, video, etc.
ch | 2024-12-11 09:30 | 2024-12-11 12:15 |  | 0.11458 | 1900-01-14 12:32 | D/T/P | Final adjustments to US, video, class diagram, etc.
wa | 2024-12-11 10:15 | 2024-12-11 12:15 |  | 0.083333 | 1900-01-14 14:32 | D/T/P | Final adjustments to US, video, etc.
ch | 2024-12-10 11:00 | 2024-12-10 14:30 |  | 0.14583 | 1900-01-14 18:02 | D/P | Working on class diagram
Formulas:
Tot Time = [End Date/Time]-[Beg Date/Time]-[Int.Time]
Tot Time = IF(COUNTBLANK([Beg Date/Time])>0,"",[End Date/Time]-[Beg Date/Time]-[Int.Time])
Run Total = [Tot Time]
Run Total = IF(COUNTBLANK([Tot Time])>0,"",[Run Total, row above]+[Tot Time])

## Individual Hours
Summary of Individual Hours
• Add your initials and name
• First person should type over my entry
Not Edittable
Automatically Calculated
Initials | Name | Total Hours
wa | William Adair | 1900-01-02 03:40
ch | Carl Hamer | 1900-01-01 19:55
mu | Miguel Uriostigue | 1900-01-01 16:00
km | Kathleen Mock | 1900-01-03 01:42
cm | Christian McCambridge | 1900-01-01 23:30
| Total | 1900-01-14 16:47
Formulas:
Total Hours = SUMIF('Time Log'!$A12:A526,[Initials],'Time Log'!$E12:E526)
Total Hours = SUM(C8:[Total Hours, row above])

## Activity Codes
Activity Codes
• You will record all time (including thinking, meetings, etc) that you spend for this project using the Time Log tab on this spreadsheet. Use the Activity Codes below to indicate how your time was spent.
Code | Task
D | Any activity related to the analysis or design, learning a technique, etc
C | Any activity related to coding
T | Any activity related to testing
P | Any activity related to presentations
O | Any other activity